Department of Technical Education

Capstone project

Format- 3

TIME-LINE SCHEDULE

| Capstone project Name: | K.A.R.M.A – Cyber Threat Deception and AI-Assisted SIEM Platform |
| --- | --- |
| Capstone project Members: | 1. Abhijeet Kumar 2. Kanaka C 3. Raghunandan T V 4. Sanjay Kashyap |

Schedule Planning & Resource Allocation

The schedule below decomposes the K.A.R.M.A work packages into practical activities, identifies resources and estimated costs, specifies dependencies and highlights the critical path. The 13-week academic schedule runs from 23 July 2026 to approximately 22 October 2026.

| WBS | Activity / Task | Start | End | Duration | Resources | Cost | Dependency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Requirements & scope finalisation | 23 Jul | 26 Jul | 3 days | 4 students, PC, project references | ₹0 | — |
| 1.2 | System architecture & module design | 27 Jul | 30 Jul | 4 days | 4 students, diagrams, PC | ₹0 | 1.1 |
| 1.3 | Technology & environment setup | 31 Jul | 02 Aug | 3 days | Python, FastAPI, Git, PC | ₹0 | 1.2 |
| 2.1 | SQLite schema & database layer | 03 Aug | 07 Aug | 5 days | Python, SQLite, PC | ₹0 | 1.3 |
| 2.2 | Core FastAPI backend & event pipeline | 08 Aug | 14 Aug | 7 days | Python, FastAPI, Uvicorn | ₹0 | 2.1 |
| 3.1 | Paramiko SSH honeypot | 10 Aug | 17 Aug | 8 days | Python, Paramiko, TCP/LAN | ₹0 | 2.2 |
| 3.2 | SSH authentication & fake shell | 15 Aug | 19 Aug | 5 days | Paramiko, Python, test client | ₹0 | 3.1 |
| 3.3 | Raw TCP FTP/Telnet/RDP decoys | 18 Aug | 24 Aug | 7 days | Python sockets, LAN, PC | ₹0 | 2.2 |
| 4.1 | FastAPI web honeypot & fake portal | 20 Aug | 27 Aug | 8 days | FastAPI, HTML/CSS/JS | ₹0 | 2.2 |
| 4.2 | Web attack pattern detection | 25 Aug | 31 Aug | 7 days | Python, HTTP testing tools | ₹0 | 4.1 |
| 4.3 | Honeytoken URLs & decoy endpoints | 01 Sep | 04 Sep | 4 days | FastAPI, SQLite, Python | ₹0 | 4.1 |
| 5.1 | MITRE ATT&CK mapping | 01 Sep | 07 Sep | 7 days | MITRE knowledge, Python | ₹0 | 2.2,3.1,4.2 |
| 5.2 | Risk score & severity engine | 05 Sep | 10 Sep | 6 days | Python, event data | ₹0 | 5.1 |
| 5.3 | Attacker profiling | 08 Sep | 12 Sep | 5 days | SQLite, Python | ₹0 | 2.1,5.2 |
| 6.1 | Application-level quarantine | 11 Sep | 15 Sep | 5 days | Python, SQLite | ₹0 | 5.2,5.3 |
| 6.2 | Manual quarantine & response testing | 16 Sep | 18 Sep | 3 days | FastAPI, dashboard API | ₹0 | 6.1 |
| 7.1 | REST API endpoints | 13 Sep | 19 Sep | 7 days | FastAPI, Python | ₹0 | 2.2,5.2 |
| 7.2 | WebSocket telemetry | 20 Sep | 23 Sep | 4 days | FastAPI WebSocket, JS | ₹0 | 7.1 |
| 7.3 | Dashboard tables & statistics | 24 Sep | 28 Sep | 5 days | HTML, CSS, JS, Chart.js | ₹0 | 7.2 |
| 7.4 | Attacker map & MITRE visualisation | 29 Sep | 02 Oct | 4 days | Leaflet, Chart.js, JS | ₹0 | 7.3 |
| 8.1 | CSV audit logging | 28 Sep | 30 Sep | 3 days | Python CSV, file system | ₹0 | 2.2 |
| 8.2 | AI threat reporting | 01 Oct | 05 Oct | 5 days | DeepSeek API, Python | ₹1,000 | 7.2,8.1 |
| 9.1 | Password strength checker | 03 Oct | 05 Oct | 3 days | HTML/CSS/JS, browser crypto | ₹0 | 7.3 |
| 9.2 | EML phishing analyser | 06 Oct | 10 Oct | 5 days | Python, email parser, .eml samples | ₹0 | 8.2 |
| 9.3 | DeepSeek phishing analysis | 08 Oct | 12 Oct | 5 days | DeepSeek API, Python | ₹500 | 9.2 |
| 10.1 | Attack simulation & test cases | 11 Oct | 14 Oct | 4 days | Sanjay Kashyap, 4 students, test environment | ₹0 | 3.3,4.2,6.2 |
| 10.2 | End-to-end integration testing | 15 Oct | 17 Oct | 3 days | Sanjay Kashyap, 4 students, test environment | ₹0 | 10.1,7.4,9.3 |
| 10.3 | Debugging & security validation | 18 Oct | 19 Oct | 2 days | Sanjay Kashyap, 4 students, test environment | ₹0 | 10.2 |
| 11.1 | Technical documentation & report | 18 Oct | 21 Oct | 4 days | 4 students, MS Word, screenshots | ₹500 | 10.3 |
| 11.2 | Presentation, demo & viva preparation | 20 Oct | 22 Oct | 3 days | 4 students, PPT, demo system | ₹500 | 11.1 |

Estimated Resource & Cost Summary

| Resource | Purpose | Estimated Cost |
| --- | --- | --- |
| Human resources | 4 students: planning, backend development, UI/UX, security QA & penetration testing, documentation and presentation | ₹0 |
| Development environment | PC/Laptop, Python, FastAPI, Uvicorn, Paramiko, SQLite, HTML/CSS/JS | ₹0 |
| Network/testing | Local LAN, TCP clients, browser and controlled attack-test scripts | ₹0 |
| AI services | DeepSeek API for AI threat/phishing analysis | ₹1,500 |
| Documentation | Printing, report preparation and submission materials | ₹500 |
| Contingency | Miscellaneous academic/project expenses | ₹500 |
| TOTAL |  | ₹2,500 |

Critical Path

Primary critical path: Requirements → Architecture → Environment Setup → Database/Core Backend → Honeypot & Detection Integration → MITRE/Risk Engine → SIEM APIs/WebSocket → Dashboard Integration → End-to-End Testing → Validation → Documentation → Final Presentation.

Parallel work packages such as the password checker, CSV logging and some toolkit modules can proceed alongside core honeypot development. Dependencies are shown in the schedule table.

13-Week Gantt Chart

| Work Package | Period | W1 23–29 Jul | W2 30 Jul–5 Aug | W3 6–12 Aug | W4 13–19 Aug | W5 20–26 Aug | W6 27 Aug–2 Sep | W7 3–9 Sep | W8 10–16 Sep | W9 17–23 Sep | W10 24–30 Sep | W11 1–7 Oct | W12 8–14 Oct | W13 15–21 Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning & Architecture | W1–W2 | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |
| Backend & Database | W2–W4 |  | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |
| SSH Honeypot | W3–W4 |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| TCP Decoys | W4–W5 |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |
| Web Honeypot | W4–W6 |  |  |  | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Honeytokens | W6–W7 |  |  |  |  |  | ■ | ■ |  |  |  |  |  |  |
| MITRE & Risk Engine | W6–W8 |  |  |  |  |  | ■ | ■ | ■ |  |  |  |  |  |
| Quarantine / Active Defense | W8–W8 |  |  |  |  |  |  |  | ■ |  |  |  |  |  |
| REST API & WebSocket | W8–W9 |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| SIEM Dashboard | W9–W10 |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| Audit & AI Reports | W10–W11 |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| Cybersecurity Toolkit | W11–W12 |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |
| Testing & Integration | W12–W13 |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |
| Documentation | W12–W13 |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |
| Presentation & Viva | W13–W13 |  |  |  |  |  |  |  |  |  |  |  |  | ■ |

Date:

| Signature of Student ________________________ | Signature of Student ________________________ | Signature of Student ________________________ | Signature of Student ________________________ |
| --- | --- | --- | --- |
| Abhijeet Kumar | Kanaka C | Raghunandan T V | Sanjay Kashyap |

Signature of the cohort owner

______________________________
Mr. Subhash J R